## Light
PROJECT: Cloud Buck Convertor
[5 empty] | Legend: | On track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned |  |  |  |  | Taken
George Li
Project start date: | 2026-05-12 |  |  |  |  | May | [20 empty] | June
Scrolling increment: | 0 | time axis 2026-05-12 to 2026-07-06
Milestone description | Category | Column1 | Progress | Start | Days | time axis 2026-05-12 to 2026-07-06
Project Definition | Milestone |  | 100% | 2026-05-12 | 1 | bar: 2026-05-12
Project Proposal | On Track |  | 100% | 2026-05-12 | 1
Research | Milestone |  | 97.5% | 2026-05-13 | 4 | bar: 2026-05-13 to 2026-05-16
Determine structure of buck convertor | On Track |  | 100% | 2026-05-13 | 2
Circuit calculations | On Track |  | 100% | 2026-05-14 | 1
Trade studies | On Track |  | 100% | 2026-05-14 | 3
Order components | On Track |  | 90% | 2026-05-16 | 1
Assembly | Milestone |  | 100% | 2026-05-19 | 2 | bar: 2026-05-19 to 2026-05-20
Assemble step down circuit | On Track |  | 100% | 2026-05-19 | 2
Assemble protection circuit | On Track |  | 100% | 2026-05-19 | 2
Testing | Milestone |  | 66.67% | 2026-05-21 | 3 | bar: 2026-05-21 to 2026-05-23
Test step down | On Track |  | 100% | 2026-05-21 | 2
Test protection | On Track |  | 100% | 2026-05-21 | 2
Integrate and test step down and protection | On Track |  | 0% | 2026-05-23 | 1
Final Prototype | Milestone |  | 60% | 2026-05-24 | 16 | bar: 2026-05-24 to 2026-06-08
Create altium schematic | On Track |  | 100% | 2026-05-24 | 2
Create altium PCB layout | On Track |  | 100% | 2026-05-25 | 2
Order PCB | On Track |  | 100% | 2026-05-26 | 1
Assemble PCB | Low Risk |  | 0% | 2026-06-06 | 2
Test PCB | Low Risk |  | 0% | 2026-06-08 | 1
Project Report | Milestone |  | 0% | 2026-06-09 | 1 | bar: 2026-06-09
Write project report | Low Risk |  | 0% | 2026-06-09 | 1