## Light
PROJECT: SLAYER Flight Computer
[5 empty] | Legend: | On track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned |  |  |  |  | Taken
George Li
Project start date: | 2026-05-12 |  |  |  |  | May | [20 empty] | June
Scrolling increment: | 0 | time axis 2026-05-12 to 2026-07-06
Milestone description | Category | Column1 | Progress | Start | Days | time axis 2026-05-12 to 2026-07-06
Project Definition | Milestone |  | 100% | 2026-05-12 | 1 | bar: 2026-05-12
Project Proposal | On Track |  | 100% | 2026-05-12 | 1
Research | Milestone |  | 100% | 2026-05-13 | 6 | bar: 2026-05-13 to 2026-05-18
Research necessary features of a flight computer | On Track |  | 100% | 2026-05-13 | 5
Research board power and protection features | On Track |  | 100% | 2026-05-13 | 5
Trade studies | On Track |  | 100% | 2026-05-17 | 2
Order components | On Track |  | 100% | 2026-05-18 | 1
T-Prototype Design | Milestone |  | 100% | 2026-05-19 | 5 | bar: 2026-05-19 to 2026-05-23
Testing prototype Altium schematic | On Track |  | 100% | 2026-05-19 | 2
Testing prototype Altium PCB layout | On Track |  | 100% | 2026-05-21 | 3
Order PCB | On Track |  | 100% | 2026-05-23 | 1
T-Prototype Assembly | Milestone |  | 0% | 2026-06-06 | 3 | bar: 2026-06-06 to 2026-06-08
Assemble sensor circuits | Low Risk |  | 0% | 2026-06-06 | 3
Assemble power circuit | Low Risk |  | 0% | 2026-06-06 | 3
T-Prototype Testing | Milestone |  | 0% | 2026-06-09 | 3 | bar: 2026-06-09 to 2026-06-11
Test sensors | Low Risk |  | 0% | 2026-06-09 | 2
Test power and protection | Low Risk |  | 0% | 2026-06-09 | 2
Document changes and problems | Low Risk |  | 0% | 2026-06-09 | 3
Final Prototype | Milestone |  | 100% | 2026-05-28 | 4 | bar: 2026-05-28 to 2026-05-31
Create altium schematic | On Track |  | 100% | 2026-05-28 | 2
Create altium PCB layout | On Track |  | 100% | 2026-05-28 | 3
Order PCB | On Track |  | 100% | 2026-05-31 | 1
F-Prototype Assembly and Testing | Milestone |  | 0% | 2026-06-12 | 3 | bar: 2026-06-12 to 2026-06-14
Assemble PCB | On Track |  | 0% | 2026-06-12 | 2
Test PCB | On Track |  | 0% | 2026-06-14 | 1
Project Report | Milestone |  | 0% | 2026-06-15 | 2 | bar: 2026-06-15 to 2026-06-16
Write project report | On Track |  | 0% | 2026-06-15 | 2